# Event Risk Assessment – KingFest25

Event: KingFest25 – Parish Winter Festival

Event Dates: Saturday 6th December 2025

Your Name: Christopher Dawes

Email Address: cdawes@kingswearparishcouncil.gov.uk

Contact Number: 07899 842 759

Company Name: Kingswear Parish Council

Persons Responsible on Site: C. Dawes, A. Payne, M. Dawes, G. Davies

Venue: Kingswear Village Hall, Priory, Church, and Square.

# Risk Assessment

| Hazard | Those at Risk | How Risk Will Be Managed | Severity (1–4) | Likelihood (1–4) | Risk Rating | Further Action Required? |
| --- | --- | --- | --- | --- | --- | --- |
| Crowd management & congestion | Public, volunteers | Clear entry/exit routes, stewards controlling flow, signage | 3 | 2 | 6 | None |
| Trips, slips & falls | Public, volunteers | Cable covers, non-slip mats near entrances, lighting checks, wet floor signage | 2 | 2 | 4 | Monitor throughout event |
| Electrical hazards (lights, PA, stalls) | Stallholders, electricians, public | No additional equipment allowed beyond that provided by Kingswear Village Hall. | 3 | 1 | 3 | Confirm all stallholders’ test certificates |
| Fire risk | Everyone | Fire extinguishers available, no open flames indoors, exits clearly marked, briefing to all staff | 4 | 1 | 4 | Fire marshal assigned (S. Partridge) |
| Food hygiene | Stallholders, public | Handwashing access, temperature control checks | 3 | 2 | 6 | Random checks on event day |
| Manual handling (stalls, tables) | Volunteers | Lifting training at briefing, use of trolleys for heavier items | 2 | 2 | 4 | Briefing before setup |
| Adverse weather (transport, outdoor stalls) | Public, volunteers | Backup indoor space (the hall), weather updates, grit paths if icy | 3 | 2 | 6 | Review forecast 72h in advance |
| Traffic & parking | Public, drivers | Marshals at entry points, signage to designated parking, liaison with local police | 3 | 2 | 6 | Confirm transport plan |
| Noise levels (music) | Public, neighbours | Limit to licensed hours, monitor sound levels | 2 | 2 | 4 | Confirm license terms |
| Child safety | Children, parents | Child wristbands, lost child procedure | 3 | 1 | 3 | On the day verify everyone up to date with policy |
| Alcohol service | Bar staff, public | Over-18 service only, Challenge 25 policy, responsible serving | 3 | 2 | 6 | License displayed on site, signs for challenge 25 |
| First aid & medical emergency | Public, volunteers | First aiders on site (C.Dawes, M. Dawes), first aid point in hall foyer, contact to 999 procedure briefed | 4 | 1 | 4 | Confirm first aid kit stock |
| Fire alarm or evacuation | Everyone | Emergency exits signed and lit, PA system for announcements, assembly point pre-briefed | 4 | 1 | 4 | None |
| COVID / communicable illness | Public, volunteers | Hand sanitiser stations, ventilation, optional masks, encourage testing if unwell | 2 | 2 | 4 | Include note in publicity |
| Security / lost property | Public | Lost property box and log, valuables at own risk notices, volunteer patrols | 1 | 2 | 2 | Record and report incidents |
| Food Allergies | Everyone | Require stall holders to comply with Natasha’s law. All food to be labelled that it may contain food allergens and that there will be cross contamination. Please to contact the event organisers for alternative options. | 4 | 1 | 4 | Ensure alternate foods and drinks that have been prepared with appropriate labelling are available in case of need. |

# Summary

Overall risk level: Medium (manageable with identified controls).

Event Manager: Christopher Dawes
Fire & Safety Lead: Christopher Dawes
First Aid Lead: Martin Dawes
Steward Lead: Martin Dawes

Signed:

Print Name: Christopher Dawes

Date: 26 October 2025

Kingswear Parish Council